TIME BREAKDOWN OF TASKS INVOLVED IN THE INVESTIGATION OF VOICE CONTROLLED WEB BROWSING FOR THE ELDERLY

Cole D. Noble

School of Electrical & Information Engineering, University of the Witwatersrand, Private Bag 3, 2050, Johannesburg, South Africa

# introduction

# key dates

A few dates were key to the completion of the project. The first set of dates is those dates allocated for meetings with the project supervisor, Mr Aveer Ramnath. These meetings helped keep the team accountable to the supervisor concerning progress on the project. These meetings also provided a platform for gaining 3rd opinion on solving/avoiding problems.

Table 1: Dates of meetings held with supervisor

|  |  |
| --- | --- |
| 6 September | Meeting 1 with Supervisor |
| 12 September | Meeting 2 with Supervisor |
| 19 September | Meeting 3 with Supervisor |
| 26 September | Meeting 4 with Supervisor |
| 3 October | Meeting 5 with Supervisor |
| 10 October | Meeting 6 with Supervisor |
| 17 October | Meeting 7 with Supervisor |

Table 2: Other key dates in project

|  |  |
| --- | --- |
| 6 September | Start project |
| 3 October | 1st Iteration due |
| 4 October | Start testing Iteration 1 |
| 6 October | Start 2nd and 3rd Iteration |
| 11 October | Start testing last two iterations |
| 21 October | Staff open day |
| 24 October | General open day |
| 27 October | Report hand in |

# individual time spent by individuals




Figure : Total hours spent on project



Figure : Time record of main events in project